## Slide 1
ERP TRANSFORMATION PROGRAM
Replacing AMG's Legacy ERP:
A 12-Month Roadmap
Structured for continuity, sequenced for risk, and built to close AMG's margin-visibility gap.
Prepared for the AMG Executive Team

## Slide 2
What We'll Cover
1
Overall Approach
Objectives, phasing, top risks and how we control scope
2
Scope & Sequencing
What's in on Day 1 and what's deliberately deferred
3
Data & Reporting
Uninterrupted KPI visibility and close continuity through the transition
AMG ERP Transformation Program
2

## Slide 3
Why This Program Matters
AMG's current landscape is fragmented, and it's costing margin.
80%
of custom orders saw margin erosion last year
20+ yrs
old legacy ERP running Finance, MRP, Procurement
5
operating locations across the US & Canada
0
reliable order-level contribution margin view today
AMG ERP Transformation Program
3

## Slide 4
Key Objectives
1
Unify the Landscape
Connect Finance, Procurement, Manufacturing, and Engineering onto a single source of truth. no more manual syncs or silos.
2
Fix BOM Accuracy
Establish a reliable Engineering BOM → Manufacturing BOM handoff for both ETO and aftermarket.
3
Restore Margin Visibility
As a direct outcome of the first two objectives — true labor, material, and overhead visibility per order.
AMG ERP Transformation Program
4

## Slide 5
Phasing Approach
Sequenced by business complexity — not a single big-bang cutover.
MONTHS 1–6
Phase 1 – Foundation
Finance, Procurement, and Aftermarket parts/service go live first — standardized, lower-risk processes that prove the platform.
MONTHS 1–6 (PARALLEL)
BOM Stabilization
The fragile Engineering-BOM sync is fixed independently, so margin erosion is addressed from day one.
MONTHS 6–12
Phase 2 – Core Operations
Manufacturing/MRP and full Engineering-BOM integration go live for the ETO business, once the platform is proven.
AMG ERP Transformation Program
5

## Slide 6
Top Risks & Mitigations
1
BOM / Data Migration
Validate & cleanse active BOMs first; archive the rest read-only.
2
Scope Creep
Standard-first build; customize only for ETO/BOM advantage.
3
User Adoption
Early power-user involvement; phase-aligned training.
4
Multi-Entity Complexity
Build consolidation into Phase 1 foundation work.
5
Cutover Disruption
Low-volume cutover window, read-only fallback, dress-rehearsal test, extra support.
AMG ERP Transformation Program
6

## Slide 7
Scope Control
Three mechanisms keep the 12-month timeline intact.
Locked Baseline
The Executive Team signs off on defined must-haves per phase before build begins. Anything else defers by default.
Standard-First Rule
Standard ERP functionality is used wherever possible. Customization is approved only for ETO/BOM handling.
Change-Control Governance
New scope requests go through a governance board and require an explicit trade-off — no addition without a cut or delay.
AMG ERP Transformation Program
7

## Slide 8
Day-1 Must-Haves
Phase 1 scope: Finance, Procurement, Aftermarket — the minimum order-to-cash chain.
✓
Order entry and tracking
✓
Inventory visibility
✓
Invoicing
✓
Payment / AR tracking
✓
Procurement & purchase orders
✓
Labor cost feed from HRIS
AMG ERP Transformation Program
8

## Slide 9
Migration Exclusions
Not all 20+ years of legacy data needs to move on Day 1.
MOVES TO THE NEW SYSTEM
• Open transactions active at go-live
• Last 1–2 years of transaction history
• Clean, validated master data (customers, vendors, active BOMs)
STAYS IN ARCHIVE (READ-ONLY)
• Closed orders / work orders older than 1–2 years
• Financial detail beyond standard reporting needs
• Inactive customer/vendor records & superseded BOM revisions
AMG ERP Transformation Program
9

## Slide 10
Customization Discipline
AMG follows a standard-first principle: the new ERP's built-in functionality is used as-is wherever possible.
Customization is approved only where it protects a genuine competitive advantage — specifically AMG's engineer-to-order and BOM processes. Everywhere else, the business adapts to the standard system rather than rebuilding it around legacy habits.
AMG ERP Transformation Program
10

## Slide 11
Data and Reporting Continuity
1
Historical Data
Recent history (1–2 yrs) migrates; older records stay in the legacy ERP, read-only and fully searchable on request.
2
Reporting During Transition
Systems stay separate — no fragile live sync. Each produces its own report; both combine into one leadership KPI dashboard.
3
Month-End Close
Close never pauses. Each phase runs a parallel close test before Finance relies on the new system alone.
AMG ERP Transformation Program
11

## Slide 12
Next Steps
Align on phasing sequence and Day-1 scope baseline
Approve the parallel BOM-stabilization workstream
Confirm governance board for change-control decisions
Thank You.
AMG ERP Transformation Program
12